## Sheet1
Application | # | Module | Activity | Task | Planned Hrs | Planned Start Date | Planned End Date | Actual Hrs | Actual Start Date | Actual End Date | Resource | Status | Remarks
HRMS | 1 | Add User, Project, Skill, Category and Civil Status | Analysis | Requirement Analysis | 1 | 2018-11-09 | 2018-11-09 | 2 | 2018-11-09 | 2018-11-09 | Jitendra, Allauddin, Viraj, Prudhviraj, Manish, Apoorva, Vinay
|  |  |  | Preparing understanding Document & Reverse Presentation | 3 | 2018-11-09 | 2018-11-09 | 3 | 2018-11-09 | 2018-11-09 | Jitendra, Allauddin, Viraj, Prudhviraj, Manish, Apoorva, Vinay
|  |  |  | Preparing QFB | 2 | 2018-11-09 | 2018-11-09 | 2 | 2018-11-09 | 2018-11-09 | Jitendra, Allauddin, Viraj, Prudhviraj, Manish, Apoorva, Vinay
|  |  |  | Understanding HLD | 1 | 2018-11-09 | 2018-11-09 | 2 | 2018-11-09 | 2018-11-09 | Jitendra, Allauddin, Viraj, Prudhviraj, Manish, Apoorva, Vinay
|  |  | Design | Unit Test Plan Preparation | 1.5 | 2018-11-12 | 2018-11-12 | 2 | 2018-11-12 | 2018-11-12 | Apoorva
|  |  |  | LLD Preparation | 1.5 | 2018-11-12 | 2018-11-12 | 2 | 2018-11-12 | 2018-11-12 | Apoorva
|  |  |  | UTP Review | 1 | 2018-11-12 | 2018-11-12 | 1 | 2018-11-12 | 2018-11-12 | Jitendra
|  |  |  | UTP Rework | 1 | 2018-11-12 | 2018-11-12 | 1 | 2018-11-12 | 2018-11-12 | Jitendra
|  |  |  | LLD Review | 1 | 2018-11-12 | 2018-11-12 | 1 | 2018-11-12 | 2018-11-12 | Prudhviraj
|  |  |  | LLD Rework | 1 | 2018-11-12 | 2018-11-12 | 1 | 2018-11-12 | 2018-11-12 | Prudhviraj
|  |  | Build | Coding | 15 | 2018-11-13 | 2018-11-13 | 20 | 2018-11-13 | 2018-11-13 | Viraj, Manish
|  |  |  | Code Self Review | 1 | 2018-11-13 | 2018-11-13 | 1 | 2018-11-13 | 2018-11-13 | Viraj, Manish
|  |  |  | Self Testing | 1 | 2018-11-13 | 2018-11-13 | 1 | 2018-11-13 | 2018-11-13 | Viraj, Manish
|  |  |  | Rework | 1 | 2018-11-13 | 2018-11-13 | 1 | 2018-11-13 | 2018-11-13 | Viraj, Manish
|  |  |  | Code Peer Review | 0.5 | 2018-11-14 | 2018-11-14 | 0.5 | 2018-11-14 | 2018-11-14 | Vinay
|  |  |  | Peer Testing | 0.5 | 2018-11-14 | 2018-11-14 | 0.5 | 2018-11-14 | 2018-11-14 | Vinay
|  |  |  | Test Result review | 0.5 | 2018-11-14 | 2018-11-14 | 0.5 | 2018-11-14 | 2018-11-14 | Allauddin
|  |  |  | Rework | 1 | 2018-11-14 | 2018-11-14 | 1 | 2018-11-14 | 2018-11-14 | Allauddin
|  |  |  | Code Integration | 1.5 | 2018-11-14 | 2018-11-14 | 1.5 | 2018-11-14 | 2018-11-14 | Jitendra, Allauddin, Viraj, Prudhviraj, Manish, Apoorva, Vinay
|  |  |  | Integration Testing | 0.5 | 2018-11-14 | 2018-11-14 | 0.5 | 2018-11-14 | 2018-11-14 | Jitendra, Allauddin, Viraj, Prudhviraj, Manish, Apoorva, Vinay
|  |  |  | Rework | 1 | 2018-11-14 | 2018-11-14 | 2 | 2018-11-14 | 2018-11-14 | Jitendra, Allauddin, Viraj, Prudhviraj, Manish, Apoorva, Vinay
|  |  |  | Test Result review | 0.5 | 2018-11-14 | 2018-11-14 | 0.5 | 2018-11-14 | 2018-11-14 | Jitendra, Allauddin, Viraj, Prudhviraj, Manish, Apoorva, Vinay
|  |  |  | Total Planned Hrs : | 38 |  | Total Actual Hrs: | 47
HRMS | 2 | Search User, Project, Skill, Category and Civil Status | Analysis | Requirement Analysis | 1 | 2018-11-09 | 2018-11-09 | 1 | 2018-11-09 | 2018-11-09 | Jitendra, Allauddin, Viraj, Prudhviraj, Manish, Apoorva, Vinay
|  |  |  | Preparing understanding Document & Reverse Presentation | 3 | 2018-11-09 | 2018-11-09 | 3 | 2018-11-09 | 2018-11-09 | Jitendra, Allauddin, Viraj, Prudhviraj, Manish, Apoorva, Vinay
|  |  |  | Preparing QFB | 2 | 2018-11-09 | 2018-11-09 | 2 | 2018-11-09 | 2018-11-09 | Jitendra, Allauddin, Viraj, Prudhviraj, Manish, Apoorva, Vinay
|  |  |  | Understanding HLD | 1 | 2018-11-09 | 2018-11-09 | 1 | 2018-11-09 | 2018-11-09 | Jitendra, Allauddin, Viraj, Prudhviraj, Manish, Apoorva, Vinay
|  |  | Design | Unit Test Plan Preparation | 1.5 | 2018-11-12 | 2018-11-12 | 2 | 2018-11-12 | 2018-11-12 | Apoorva
|  |  |  | LLD Preparation | 1.5 | 2018-11-12 | 2018-11-12 | 2 | 2018-11-12 | 2018-11-12 | Apoorva
|  |  |  | UTP Review | 1 | 2018-11-12 | 2018-11-12 | 1 | 2018-11-12 | 2018-11-12 | Jitendra
|  |  |  | UTP Rework | 1 | 2018-11-12 | 2018-11-12 | 1 | 2018-11-12 | 2018-11-12 | Jitendra
|  |  |  | LLD Review | 1 | 2018-11-12 | 2018-11-12 | 1 | 2018-11-12 | 2018-11-12 | Prudhviraj
|  |  |  | LLD Rework | 1 | 2018-11-12 | 2018-11-12 | 1 | 2018-11-12 | 2018-11-12 | Prudhviraj
|  |  | Build | Coding | 15 | 2018-11-13 | 2018-11-13 | 18 | 2018-11-13 | 2018-11-13 | Viraj, Manish
|  |  |  | Code Self Review | 1 | 2018-11-13 | 2018-11-13 | 1 | 2018-11-13 | 2018-11-13 | Viraj, Manish
|  |  |  | Self Testing | 1 | 2018-11-13 | 2018-11-13 | 1 | 2018-11-13 | 2018-11-13 | Viraj, Manish
|  |  |  | Rework | 1 | 2018-11-13 | 2018-11-13 | 1 | 2018-11-13 | 2018-11-13 | Viraj, Manish
|  |  |  | Code Peer Review | 0.5 | 2018-11-14 | 2018-11-14 | 0.5 | 2018-11-14 | 2018-11-14 | Vinay
|  |  |  | Peer Testing | 0.5 | 2018-11-14 | 2018-11-14 | 0.5 | 2018-11-14 | 2018-11-14 | Vinay
|  |  |  | Test Result review | 0.5 | 2018-11-14 | 2018-11-14 | 0.5 | 2018-11-14 | 2018-11-14 | Allauddin
|  |  |  | Rework | 1 | 2018-11-14 | 2018-11-14 | 1 | 2018-11-14 | 2018-11-14 | Allauddin
|  |  |  | Code Integration | 1.5 | 2018-11-14 | 2018-11-14 | 1.5 | 2018-11-14 | 2018-11-14 | Jitendra, Allauddin, Viraj, Prudhviraj, Manish, Apoorva, Vinay
|  |  |  | Integration Testing | 0.5 | 2018-11-14 | 2018-11-14 | 0.5 | 2018-11-14 | 2018-11-14 | Jitendra, Allauddin, Viraj, Prudhviraj, Manish, Apoorva, Vinay
|  |  |  | Rework | 1 | 2018-11-14 | 2018-11-14 | 1 | 2018-11-14 | 2018-11-14 | Jitendra, Allauddin, Viraj, Prudhviraj, Manish, Apoorva, Vinay
|  |  |  | Test Result review | 0.5 | 2018-11-14 | 2018-11-14 | 0.5 | 2018-11-14 | 2018-11-14 | Jitendra, Allauddin, Viraj, Prudhviraj, Manish, Apoorva, Vinay
|  |  |  | Total Planned Hrs : | 38 | 2018-11-23 | Total Actual Hrs: | 42
HRMS | 3 | Update User, Project, Skill, Category and Civil Status | Analysis | Requirement Analysis | 1 | 2018-11-09 | 2018-11-09 | 1 | 2018-11-09 | 2018-11-09 | Jitendra, Allauddin, Viraj, Prudhviraj, Manish, Apoorva, Vinay
|  |  |  | Preparing understanding Document & Reverse Presentation | 3 | 2018-11-09 | 2018-11-09 | 3 | 2018-11-09 | 2018-11-09 | Jitendra, Allauddin, Viraj, Prudhviraj, Manish, Apoorva, Vinay
|  |  |  | Preparing QFB | 2 | 2018-11-09 | 2018-11-09 | 2 | 2018-11-09 | 2018-11-09 | Jitendra, Allauddin, Viraj, Prudhviraj, Manish, Apoorva, Vinay
|  |  |  | Understanding HLD | 1 | 2018-11-09 | 2018-11-09 | 1 | 2018-11-09 | 2018-11-09 | Jitendra, Allauddin, Viraj, Prudhviraj, Manish, Apoorva, Vinay
|  |  | Design | Unit Test Plan Preparation | 1.5 | 2018-11-12 | 2018-11-12 | 2 | 2018-11-12 | 2018-11-12 | Apoorva
|  |  |  | LLD Preparation | 1.5 | 2018-11-12 | 2018-11-12 | 2 | 2018-11-12 | 2018-11-12 | Apoorva
|  |  |  | UTP Review | 1 | 2018-11-12 | 2018-11-12 | 1 | 2018-11-12 | 2018-11-12 | Jitendra
|  |  |  | UTP Rework | 1 | 2018-11-12 | 2018-11-12 | 1 | 2018-11-12 | 2018-11-12 | Jitendra
|  |  |  | LLD Review | 1 | 2018-11-12 | 2018-11-12 | 1 | 2018-11-12 | 2018-11-12 | Prudhviraj
|  |  |  | LLD Rework | 1 | 2018-11-12 | 2018-11-12 | 1 | 2018-11-12 | 2018-11-12 | Prudhviraj
|  |  | Build | Coding | 15 | 2018-11-13 | 2018-11-13 | 17 | 2018-11-13 | 2018-11-13 | Viraj, Manish
|  |  |  | Code Self Review | 1 | 2018-11-13 | 2018-11-13 | 1 | 2018-11-13 | 2018-11-13 | Viraj, Manish
|  |  |  | Self Testing | 1 | 2018-11-13 | 2018-11-13 | 1 | 2018-11-13 | 2018-11-13 | Viraj, Manish
|  |  |  | Rework | 1 | 2018-11-13 | 2018-11-13 | 1 | 2018-11-13 | 2018-11-13 | Viraj, Manish
|  |  |  | Code Peer Review | 0.5 | 2018-11-14 | 2018-11-14 | 0.5 | 2018-11-14 | 2018-11-14 | Vinay
|  |  |  | Peer Testing | 0.5 | 2018-11-14 | 2018-11-14 | 0.5 | 2018-11-14 | 2018-11-14 | Vinay
|  |  |  | Test Result review | 0.5 | 2018-11-14 | 2018-11-14 | 0.5 | 2018-11-14 | 2018-11-14 | Allauddin
|  |  |  | Rework | 1 | 2018-11-14 | 2018-11-14 | 1 | 2018-11-14 | 2018-11-14 | Allauddin
|  |  |  | Code Integration | 1.5 | 2018-11-14 | 2018-11-14 | 1.5 | 2018-11-14 | 2018-11-14 | Jitendra, Allauddin, Viraj, Prudhviraj, Manish, Apoorva, Vinay
|  |  |  | Integration Testing | 0.5 | 2018-11-14 | 2018-11-14 | 0.5 | 2018-11-14 | 2018-11-14 | Jitendra, Allauddin, Viraj, Prudhviraj, Manish, Apoorva, Vinay
|  |  |  | Rework | 1 | 2018-11-14 | 2018-11-14 | 1 | 2018-11-14 | 2018-11-14 | Jitendra, Allauddin, Viraj, Prudhviraj, Manish, Apoorva, Vinay
|  |  |  | Test Result review | 0.5 | 2018-11-14 | 2018-11-14 | 0.5 | 2018-11-14 | 2018-11-14 | Jitendra, Allauddin, Viraj, Prudhviraj, Manish, Apoorva, Vinay
|  |  |  | Total Planned Hrs : | 38 | 2018-11-17 | Total Actual Hrs: | 41
HRMS | 4 | Delete User, Project, Skill, Category and Civil Status | Analysis | Requirement Analysis | 1 | 2018-11-09 | 2018-11-09 | 1 | 2018-11-09 | 2018-11-09 | Jitendra, Allauddin, Viraj, Prudhviraj, Manish, Apoorva, Vinay
|  |  |  | Preparing understanding Document & Reverse Presentation | 3 | 2018-11-09 | 2018-11-09 | 3 | 2018-11-09 | 2018-11-09 | Jitendra, Allauddin, Viraj, Prudhviraj, Manish, Apoorva, Vinay
|  |  |  | Preparing QFB | 2 | 2018-11-09 | 2018-11-09 | 2 | 2018-11-09 | 2018-11-09 | Jitendra, Allauddin, Viraj, Prudhviraj, Manish, Apoorva, Vinay
|  |  |  | Understanding HLD | 1 | 2018-11-09 | 2018-11-09 | 1 | 2018-11-09 | 2018-11-09 | Jitendra, Allauddin, Viraj, Prudhviraj, Manish, Apoorva, Vinay
|  |  | Design | Unit Test Plan Preparation | 1.5 | 2018-11-12 | 2018-11-12 | 2 | 2018-11-12 | 2018-11-12 | Apoorva
|  |  |  | LLD Preparation | 1.5 | 2018-11-12 | 2018-11-12 | 2 | 2018-11-12 | 2018-11-12 | Apoorva
|  |  |  | UTP Review | 1 | 2018-11-12 | 2018-11-12 | 1 | 2018-11-12 | 2018-11-12 | Jitendra
|  |  |  | UTP Rework | 1 | 2018-11-12 | 2018-11-12 | 1 | 2018-11-12 | 2018-11-12 | Jitendra
|  |  |  | LLD Review | 1 | 2018-11-12 | 2018-11-12 | 1 | 2018-11-12 | 2018-11-12 | Prudhviraj
|  |  |  | LLD Rework | 1 | 2018-11-12 | 2018-11-12 | 1 | 2018-11-12 | 2018-11-12 | Prudhviraj
|  |  | Build | Coding | 15 | 2018-11-13 | 2018-11-13 | 15 | 2018-11-13 | 2018-11-13 | Viraj, Manish
|  |  |  | Code Self Review | 1 | 2018-11-13 | 2018-11-13 | 1 | 2018-11-13 | 2018-11-13 | Viraj, Manish
|  |  |  | Self Testing | 1 | 2018-11-13 | 2018-11-13 | 1 | 2018-11-13 | 2018-11-13 | Viraj, Manish
|  |  |  | Rework | 1 | 2018-11-13 | 2018-11-13 | 1 | 2018-11-13 | 2018-11-13 | Viraj, Manish
|  |  |  | Code Peer Review | 0.5 | 2018-11-14 | 2018-11-14 | 0.5 | 2018-11-14 | 2018-11-14 | Vinay
|  |  |  | Peer Testing | 0.5 | 2018-11-14 | 2018-11-14 | 0.5 | 2018-11-14 | 2018-11-14 | Vinay
|  |  |  | Test Result review | 0.5 | 2018-11-14 | 2018-11-14 | 0.5 | 2018-11-14 | 2018-11-14 | Allauddin
|  |  |  | Rework | 1 | 2018-11-14 | 2018-11-14 | 1 | 2018-11-14 | 2018-11-14 | Allauddin
|  |  |  | Code Integration | 1.5 | 2018-11-14 | 2018-11-14 | 1.5 | 2018-11-14 | 2018-11-14 | Jitendra, Allauddin, Viraj, Prudhviraj, Manish, Apoorva, Vinay
|  |  |  | Integration Testing | 0.5 | 2018-11-14 | 2018-11-14 | 0.5 | 2018-11-14 | 2018-11-14 | Jitendra, Allauddin, Viraj, Prudhviraj, Manish, Apoorva, Vinay
|  |  |  | Rework | 1 | 2018-11-14 | 2018-11-14 | 1 | 2018-11-14 | 2018-11-14 | Jitendra, Allauddin, Viraj, Prudhviraj, Manish, Apoorva, Vinay
|  |  |  | Test Result review | 0.5 | 2018-11-14 | 2018-11-14 | 0.5 | 2018-11-14 | 2018-11-14 | Jitendra, Allauddin, Viraj, Prudhviraj, Manish, Apoorva, Vinay
|  |  |  | Total Planned Hrs : | 38 | 2018-11-11 | Total Actual Hrs: | 39
HRMS | 5 | Display User, Project, Skill, Category and Civil Status | Analysis | Requirement Analysis | 1 | 2018-11-09 | 2018-11-09 | 1 | 2018-11-09 | 2018-11-09 | Jitendra, Allauddin, Viraj, Prudhviraj, Manish, Apoorva, Vinay
|  |  |  | Preparing understanding Document & Reverse Presentation | 3 | 2018-11-09 | 2018-11-09 | 3 | 2018-11-09 | 2018-11-09 | Jitendra, Allauddin, Viraj, Prudhviraj, Manish, Apoorva, Vinay
|  |  |  | Preparing QFB | 2 | 2018-11-09 | 2018-11-09 | 2 | 2018-11-09 | 2018-11-09 | Jitendra, Allauddin, Viraj, Prudhviraj, Manish, Apoorva, Vinay
|  |  |  | Understanding HLD | 1 | 2018-11-09 | 2018-11-09 | 1 | 2018-11-09 | 2018-11-09 | Jitendra, Allauddin, Viraj, Prudhviraj, Manish, Apoorva, Vinay
|  |  | Design | Unit Test Plan Preparation | 1.5 | 2018-11-12 | 2018-11-12 | 2 | 2018-11-12 | 2018-11-12 | Apoorva
|  |  |  | LLD Preparation | 1.5 | 2018-11-12 | 2018-11-12 | 2 | 2018-11-12 | 2018-11-12 | Apoorva
|  |  |  | UTP Review | 1 | 2018-11-12 | 2018-11-12 | 1 | 2018-11-12 | 2018-11-12 | Jitendra
|  |  |  | UTP Rework | 1 | 2018-11-12 | 2018-11-12 | 1 | 2018-11-12 | 2018-11-12 | Jitendra
|  |  |  | LLD Review | 1 | 2018-11-12 | 2018-11-12 | 1 | 2018-11-12 | 2018-11-12 | Prudhviraj
|  |  |  | LLD Rework | 1 | 2018-11-12 | 2018-11-12 | 1 | 2018-11-12 | 2018-11-12 | Prudhviraj
|  |  | Build | Coding | 15 | 2018-11-13 | 2018-11-13 | 15 | 2018-11-13 | 2018-11-13 | Viraj, Manish
|  |  |  | Code Self Review | 1 | 2018-11-13 | 2018-11-13 | 1 | 2018-11-13 | 2018-11-13 | Viraj, Manish
|  |  |  | Self Testing | 1 | 2018-11-13 | 2018-11-13 | 1 | 2018-11-13 | 2018-11-13 | Viraj, Manish
|  |  |  | Rework | 1 | 2018-11-13 | 2018-11-13 | 1 | 2018-11-13 | 2018-11-13 | Viraj, Manish
|  |  |  | Code Peer Review | 0.5 | 2018-11-14 | 2018-11-14 | 0.5 | 2018-11-14 | 2018-11-14 | Vinay
|  |  |  | Peer Testing | 0.5 | 2018-11-14 | 2018-11-14 | 0.5 | 2018-11-14 | 2018-11-14 | Vinay
|  |  |  | Test Result review | 0.5 | 2018-11-14 | 2018-11-14 | 0.5 | 2018-11-14 | 2018-11-14 | Allauddin
|  |  |  | Rework | 1 | 2018-11-14 | 2018-11-14 | 1 | 2018-11-14 | 2018-11-14 | Allauddin
|  |  |  | Code Integration | 1.5 | 2018-11-14 | 2018-11-14 | 1.5 | 2018-11-14 | 2018-11-14 | Jitendra, Allauddin, Viraj, Prudhviraj, Manish, Apoorva, Vinay
|  |  |  | Integration Testing | 0.5 | 2018-11-14 | 2018-11-14 | 0.5 | 2018-11-14 | 2018-11-14 | Jitendra, Allauddin, Viraj, Prudhviraj, Manish, Apoorva, Vinay
|  |  |  | Rework | 1 | 2018-11-14 | 2018-11-14 | 1 | 2018-11-14 | 2018-11-14 | Jitendra, Allauddin, Viraj, Prudhviraj, Manish, Apoorva, Vinay
|  |  |  | Test Result review | 0.5 | 2018-11-14 | 2018-11-14 | 0.5 | 2018-11-14 | 2018-11-14 | Jitendra, Allauddin, Viraj, Prudhviraj, Manish, Apoorva, Vinay
|  |  |  | Total Planned Hrs : | 38 | 2018-11-05 | Total Actual Hrs: | 39
HRMS | 6 | Login | Analysis | Requirement Analysis | 1 | 2018-11-09 | 2018-11-09 | 1 | 2018-11-09 | 2018-11-09 | Jitendra, Allauddin, Viraj, Prudhviraj, Manish, Apoorva, Vinay
|  |  |  | Preparing understanding Document & Reverse Presentation | 3 | 2018-11-09 | 2018-11-09 | 3 | 2018-11-09 | 2018-11-09 | Jitendra, Allauddin, Viraj, Prudhviraj, Manish, Apoorva, Vinay
|  |  |  | Preparing QFB | 2 | 2018-11-09 | 2018-11-09 | 2 | 2018-11-09 | 2018-11-09 | Jitendra, Allauddin, Viraj, Prudhviraj, Manish, Apoorva, Vinay
|  |  |  | Understanding HLD | 1 | 2018-11-09 | 2018-11-09 | 1 | 2018-11-09 | 2018-11-09 | Jitendra, Allauddin, Viraj, Prudhviraj, Manish, Apoorva, Vinay
|  |  | Design | Unit Test Plan Preparation | 1.5 | 2018-11-12 | 2018-11-12 | 2 | 2018-11-12 | 2018-11-12 | Apoorva
|  |  |  | LLD Preparation | 1.5 | 2018-11-12 | 2018-11-12 | 2 | 2018-11-12 | 2018-11-12 | Apoorva
|  |  |  | UTP Review | 1 | 2018-11-12 | 2018-11-12 | 1 | 2018-11-12 | 2018-11-12 | Jitendra
|  |  |  | UTP Rework | 1 | 2018-11-12 | 2018-11-12 | 1 | 2018-11-12 | 2018-11-12 | Jitendra
|  |  |  | LLD Review | 1 | 2018-11-12 | 2018-11-12 | 1 | 2018-11-12 | 2018-11-12 | Prudhviraj
|  |  |  | LLD Rework | 1 | 2018-11-12 | 2018-11-12 | 1 | 2018-11-12 | 2018-11-12 | Prudhviraj
|  |  | Build | Coding | 15 | 2018-11-13 | 2018-11-13 | 14 | 2018-11-13 | 2018-11-13 | Viraj, Manish
|  |  |  | Code Self Review | 1 | 2018-11-13 | 2018-11-13 | 1 | 2018-11-13 | 2018-11-13 | Viraj, Manish
|  |  |  | Self Testing | 1 | 2018-11-13 | 2018-11-13 | 1 | 2018-11-13 | 2018-11-13 | Viraj, Manish
|  |  |  | Rework | 1 | 2018-11-13 | 2018-11-13 | 1 | 2018-11-13 | 2018-11-13 | Viraj, Manish
|  |  |  | Code Peer Review | 0.5 | 2018-11-14 | 2018-11-14 | 0.5 | 2018-11-14 | 2018-11-14 | Vinay
|  |  |  | Peer Testing | 0.5 | 2018-11-14 | 2018-11-14 | 0.5 | 2018-11-14 | 2018-11-14 | Vinay
|  |  |  | Test Result review | 0.5 | 2018-11-14 | 2018-11-14 | 0.5 | 2018-11-14 | 2018-11-14 | Allauddin
|  |  |  | Rework | 1 | 2018-11-14 | 2018-11-14 | 1 | 2018-11-14 | 2018-11-14 | Allauddin
|  |  |  | Code Integration | 1.5 | 2018-11-14 | 2018-11-14 | 1.5 | 2018-11-14 | 2018-11-14 | Jitendra, Allauddin, Viraj, Prudhviraj, Manish, Apoorva, Vinay
|  |  |  | Integration Testing | 0.5 | 2018-11-14 | 2018-11-14 | 0.5 | 2018-11-14 | 2018-11-14 | Jitendra, Allauddin, Viraj, Prudhviraj, Manish, Apoorva, Vinay
|  |  |  | Rework | 1 | 2018-11-14 | 2018-11-14 | 1 | 2018-11-14 | 2018-11-14 | Jitendra, Allauddin, Viraj, Prudhviraj, Manish, Apoorva, Vinay
|  |  |  | Test Result review | 0.5 | 2018-11-14 | 2018-11-14 | 0.5 | 2018-11-14 | 2018-11-14 | Jitendra, Allauddin, Viraj, Prudhviraj, Manish, Apoorva, Vinay
|  |  |  | Total Planned Hrs : | 38 | 2018-11-29 | Total Actual Hrs: | 38
HRMS | 7 | Sign Up | Analysis | Requirement Analysis | 1 | 2018-11-09 | 2018-11-09 | 1 | 2018-11-09 | 2018-11-09 | Jitendra, Allauddin, Viraj, Prudhviraj, Manish, Apoorva, Vinay
|  |  |  | Preparing understanding Document & Reverse Presentation | 3 | 2018-11-09 | 2018-11-09 | 3 | 2018-11-09 | 2018-11-09 | Jitendra, Allauddin, Viraj, Prudhviraj, Manish, Apoorva, Vinay
|  |  |  | Preparing QFB | 2 | 2018-11-09 | 2018-11-09 | 2 | 2018-11-09 | 2018-11-09 | Jitendra, Allauddin, Viraj, Prudhviraj, Manish, Apoorva, Vinay
|  |  |  | Understanding HLD | 1 | 2018-11-09 | 2018-11-09 | 1 | 2018-11-09 | 2018-11-09 | Jitendra, Allauddin, Viraj, Prudhviraj, Manish, Apoorva, Vinay
|  |  | Design | Unit Test Plan Preparation | 1.5 | 2018-11-12 | 2018-11-12 | 2 | 2018-11-12 | 2018-11-12 | Apoorva
|  |  |  | LLD Preparation | 1.5 | 2018-11-12 | 2018-11-12 | 2 | 2018-11-12 | 2018-11-12 | Apoorva
|  |  |  | UTP Review | 1 | 2018-11-12 | 2018-11-12 | 1 | 2018-11-12 | 2018-11-12 | Jitendra
|  |  |  | UTP Rework | 1 | 2018-11-12 | 2018-11-12 | 1 | 2018-11-12 | 2018-11-12 | Jitendra
|  |  |  | LLD Review | 1 | 2018-11-12 | 2018-11-12 | 1 | 2018-11-12 | 2018-11-12 | Prudhviraj
|  |  |  | LLD Rework | 1 | 2018-11-12 | 2018-11-12 | 1 | 2018-11-12 | 2018-11-12 | Prudhviraj
|  |  | Build | Coding | 15 | 2018-11-13 | 2018-11-13 | 14 | 2018-11-13 | 2018-11-13 | Viraj, Manish
|  |  |  | Code Self Review | 1 | 2018-11-13 | 2018-11-13 | 1 | 2018-11-13 | 2018-11-13 | Viraj, Manish
|  |  |  | Self Testing | 1 | 2018-11-13 | 2018-11-13 | 1 | 2018-11-13 | 2018-11-13 | Viraj, Manish
|  |  |  | Rework | 1 | 2018-11-13 | 2018-11-13 | 1 | 2018-11-13 | 2018-11-13 | Viraj, Manish
|  |  |  | Code Peer Review | 0.5 | 2018-11-14 | 2018-11-14 | 0.5 | 2018-11-14 | 2018-11-14 | Vinay
|  |  |  | Peer Testing | 0.5 | 2018-11-14 | 2018-11-14 | 0.5 | 2018-11-14 | 2018-11-14 | Vinay
|  |  |  | Test Result review | 0.5 | 2018-11-14 | 2018-11-14 | 0.5 | 2018-11-14 | 2018-11-14 | Allauddin
|  |  |  | Rework | 1 | 2018-11-14 | 2018-11-14 | 1 | 2018-11-14 | 2018-11-14 | Allauddin
|  |  |  | Code Integration | 1.5 | 2018-11-14 | 2018-11-14 | 1.5 | 2018-11-14 | 2018-11-14 | Jitendra, Allauddin, Viraj, Prudhviraj, Manish, Apoorva, Vinay
|  |  |  | Integration Testing | 0.5 | 2018-11-14 | 2018-11-14 | 0.5 | 2018-11-14 | 2018-11-14 | Jitendra, Allauddin, Viraj, Prudhviraj, Manish, Apoorva, Vinay
|  |  |  | Rework | 1 | 2018-11-14 | 2018-11-14 | 1 | 2018-11-14 | 2018-11-14 | Jitendra, Allauddin, Viraj, Prudhviraj, Manish, Apoorva, Vinay
|  |  |  | Test Result review | 0.5 | 2018-11-14 | 2018-11-14 | 0.5 | 2018-11-14 | 2018-11-14 | Jitendra, Allauddin, Viraj, Prudhviraj, Manish, Apoorva, Vinay
|  |  |  | Total Planned Hrs : | 38 |  | Total Actual Hrs: | 38
|  | Presentation Preparation |  | Presentation Preparation | 3 | 2018-11-15 | 2018-11-15 | 4 | 2018-11-15 | 2018-11-15
|  |  |  | Deployment | 1 | 2018-11-15 | 2018-11-15 | 1 | 2018-11-15 | 2018-11-15
Note on C74: Nath, Apoorva: