## Sheet1
Minutes of Meeting
Project Name | HR Management System | Project Code
Project Manager
Group | Group-4 | Date | 2018-11-09
Attendees | 7 | Start Time | 9:15
Absence intimated | None | End Time | 9:45
Absent | None | Venue | Training centre
Chaired by | Apoorva Nath
Minutes by | Prudhviraj Cirikonda
Agenda
Introductory session.
S.No. | Action Item Description | Responsibility | Planned closure date
1 | Send all the documents till the coding phase to the mentor. | Apoorva Nath | 2018-11-09
2 | Prepare reverse document | Manish Rahangdale, Viraj Dere, Apoorva Nath, Prudhviraj Cirikonda, Vinay Samudrala,Mohammed Allauddin Shaik, Jitendra Sai Pandava | 2018-11-09
S.No. | Minutes
1 | Introduction of team members and project manager.
S.No. | Decisions Made (Pls Indicate Deferred Decisions too and the Reason)
Next Meeting Venue |  |  | Date
Yet to decide