## Sheet1
Minutes of Meeting
Project Name | HR Management System | Project Code
Project Manager
Group | Group-4 | Date | 2018-11-13
Attendees | 7 | Start Time | 9:15
Absence intimated | None | End Time | 9:45
Absent | None | Venue | Training centre
Chaired by | Manish Rahangdale
Minutes by | Vinay Samudrala
Agenda
Checking the reworked documents and feedbacks about the documents.
S.No. | Action Item Description | Responsibility | Planned closure date
1 | Send the UTPs | Manish Rahangdale | 2018-11-13
2 | Modify the reworked LLDs, Tracebility , Understanding document. | Manish Rahangdale, Viraj Dere, Apoorva Nath, Prudhviraj Cirikonda, Vinay Samudrala,Mohammed Allauddin Shaik, Jitendra Sai Pandava | 2018-11-13
S.No. | Minutes
1 | Feedback about the reworked documents.
S.No. | Decisions Made (Pls Indicate Deferred Decisions too and the Reason)
1 | Modify the reworked LLD and understanding documents as instructed.
2 | Send the UTPs
Next Meeting Venue |  |  | Date
Yet to decide