## Sheet1
HR Management System
Daily Time Sheet for : Vinay Samudrala |  | Main Task(Prep.) | 161700-EMS-Time Sheet | [27 empty] | Month : |  |  | 2018-11-01
Task Desc |  | Task Category | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | Total
| Phase |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Available Hrs |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24
Over Time |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5
Total Hrs. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 9 | 9.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.5
0
Understanding the Case study | Requirements | Main Task(Prep.) | [31 empty] | 1 | bar: 161700-EMS-Time Sheet F 9
Requirement Analysis | Requirements | Main Task(Prep.) | 161700-EMS-Time Sheet F 9: 2 | 2
Preparing understanding Document & Reverse Presentation | Requirements | Main Task(Prep.) | 161700-EMS-Time Sheet F 9: 3 | 3
Preparing QFB | Requirements | Main Task(Prep.) | [31 empty] | 1 | bar: 161700-EMS-Time Sheet F 9
Understanding HLD | Requirements | Main Task(Prep.) | [31 empty] | 1 | bar: 161700-EMS-Time Sheet F 9
Unit Test Plan Preparation | Unit Testing | Main Task(Prep.) | 161700-EMS-Time Sheet M 12: 2 | 2
LLD Preparation | Low Level Design | Main Task(Prep.) | [31 empty] | 1 | bar: 161700-EMS-Time Sheet M 12
UTP Review | Training | Review | 161700-EMS-Time Sheet M 12: 3 | 2
UTP Rework | Unit Testing | Review | 161700-EMS-Time Sheet M 12: 2 | 2
LLD Review | Low Level Design | Review | 161700-EMS-Time Sheet M 12: 0.5 | 0.5
LLD Rework | Low Level Design | Review | 161700-EMS-Time Sheet M 12: 0.5 | 0.5
Coding | Coding | Main Task(Prep.) | 161700-EMS-Time Sheet T 13: 6 | 6
Code Self Review | Coding | Main Task(Prep.) | [31 empty] | 1 | bar: 161700-EMS-Time Sheet T 13
Self Testing | Coding | Main Task(Prep.) | [31 empty] | 1 | bar: 161700-EMS-Time Sheet T 13
Rework | Coding | Rework | 161700-EMS-Time Sheet T 13: 1.5 | 1.5
Code Peer Review | Unit Testing | Review | [31 empty] | 0
Peer Testing | Unit Testing | Rework | [31 empty] | 0
Test Result review | Unit Testing | Review | [31 empty] | 0
Rework | Coding | Rework | [31 empty] | 0
Code Integration | Coding | Main Task(Prep.) | [31 empty] | 0
Integration Testing | Training | Main Task(Prep.) | [31 empty] | 0
Rework | Coding | Rework | [31 empty] | 0
Test Result review | Coding | Review | [31 empty] | 0
Presentation Preparation | Miscellaneous | Main Task(Prep.) | [31 empty] | 0
Deployment | Release | Main Task(Prep.) | [31 empty] | 0
Note on AI2: Month Start Date. Please enter Month start date. (e.g. 01 Aug 02)
Note on AI7: Total Effort for the Month
Note on A8: 500155: Enter Description of the task For Ex MRID, PP Preparation, Metrics Preparation etc...
Note on C8: Leave will not be accounted in the Totals.