## Sheet1
S.No | DATE | DAY | Description of the Activity | Deliverables
1 | 2018-11-09 | Friday | Creating Groups . Providing Case Study. TFS folder structure creation
2 | 2018-11-09 | Friday | Prepare Understanding Document based on case study. Providing URS & Reverse Presentation | Understanding Document
3 | 2018-11-10 | Saturday
4 | 2018-11-11 | Sunday
5 | 2018-11-12 | Monday | Trainees will send the Query FeedBack form to mentors/training Dept. HLD artifacts given to trainees. | QFB
6 | 2018-11-12 | Monday | Query clarification by mentors/Training dept. UTP Preparation | QFB with client response, UTP
7 | 2018-11-12 | Monday | WBS preparation. Prepare LLD | LLD & WBS
8 | 2018-11-12 | Monday | UTP Review & Rework
9 | 2018-11-12 | Monday | LLD Review & Rework | Baselined Testcases and LLD
10 | 2018-11-13 | Tuesday | Coding
11 | 2018-11-13 | Tuesday | Coding
12 | 2018-11-13 | Tuesday | Coding
13 | 2018-11-13 | Tuesday | Coding | Unit Code
14 | 2018-11-14 | Wednesday | Self Testing & Self Review
15 | 2018-11-14 | Wednesday | Rework
16 | 2018-11-14 | Wednesday | Peer Testing & Peer Review | Reviewed code
17 | 2018-11-14 | Wednesday | Rework | Reworked Code
18 | 2018-11-14 | Wednesday | Code Integration, Testing & Rework | Delivarable Code
19 | 2018-11-15 | Thursday | Demo to Mentors, Preparation for presentation | Presentation
20 | 2018-11-15 | Thursday | Final Presentation